CTP PLANNER

Building + Curing Synchronized Scheduling Engine

Complete Working Explainer  |  Hinglish  |  Management Briefing

PCR  &  TBR  Plants   |   Reference Month: August 2026

| Document | Detail |
| --- | --- |
| Purpose | CTP Planner ka poora working — architecture, layers, inputs, flow, results |
| Audience | Management / Plant Planning Head / Review Committee |
| Language | Hinglish (Hindi + English technical terms) |
| Engine | planner/cmbc/ (LIVE engine) — driven by main.py |
| Reference run | runs/FINAL_aug (month = 2026-08) |
| Data basis | Saare numbers actual run artefacts (parquet) se nikale gaye hain |

# 0.  Executive Summary - Ek Page Mein Poori Kahani

CTP Planner ek Python-based scheduling engine hai jo do plants - PCR (Passenger Car Radial) aur TBR (Truck Bus Radial) - ke liye poore mahine ka synchronized Building + Curing schedule banata hai. Input aata hai plant ke demand workbook aur master files se; output jaata hai BTP pack (Excel) aur 13-sheet shift schedule ke roop mein.

Sabse important baat jo samajhni hai - yeh plant CURING-FIRST hai:

Curing proposes, Building disposes Pehle CURING campaign place hota hai (kaunse press pe, kaunsa GT, kab se kab tak). Uske BAAD building ko ULTA (backwards) release kiya jaata hai - yaani t_cure minus tau* minus build_duration. Building leader nahi hai, follower hai. Green Tyre (GT) sirf 72 ghante chalta hai (rule R5), isliye GT ek SYNCHRONIZATION BUFFER hai - production target NAHI hai. Zyada GT banana matlab tyre kharab hona.

August 2026 ka actual result (run: FINAL_aug):

| Metric | PCR | TBR | Comment |
| --- | --- | --- | --- |
| Demand (tyres) | 4,29,146 | 99,019 | Plant ka order book |
| L5 ne cure campaign place kiya | 4,12,897 | 98,625 | Press capacity ki wajah se kam |
| BUILT (actual banaya) | 4,08,950 | 97,985 | Yeh REAL production number hai |
| Cured in-month (fed) | 3,84,464 | 92,983 | Month ke andar press mein gaya |
| Build machine utilisation | 83.5 % | 81.7 % | ~17-18 % capacity khaali padi hai |
| Press utilisation | 102.6 % | 100.4 % | Month se BAHAR tak chal raha hai |
| Build capacity ceiling | 5,02,839 (117 %) | 1,17,572 (119 %) | Building bottleneck NAHI hai |
| Cure capacity ceiling (model) | 4,07,396 (95 %) | 1,06,415 (107 %) | PCR yahan phansa hua hai |

Teen line ka nichod:

PCR mein hum 4 lakh se ZYADA bana rahe hain (4,08,950). Jo poora nahi ho raha woh 4,29,146 ka demand hai.

Building bottleneck NAHI hai - uske paas 17 % capacity khaali padi hai. Asli deewar CURING hai.

Mahine ke SHURU aur ANT mein jo dip dikhta hai woh lagbhag poora PCR shortfall explain kar deta hai (dip loss ~16,346 tyres vs total gap 16,249 tyres). Section 8 mein poora hisaab hai.

# 1.  CTP Planner Hai Kya - Problem Statement

## 1.1  Problem kya solve kar rahe hain

Tyre plant mein do main production stages hain jo aapas mein jude hue hain:

BUILDING (TBM machines) - yahan Green Tyre (GT) banta hai. Kachcha tyre, abhi cure nahi hua.

CURING (Press) - yahan GT ko heat + pressure se pakaaya jaata hai, finished tyre banta hai.

Beech mein GT inventory hai. Problem yeh hai ki GT sirf 72 ghante tak use ho sakta hai. Zyada bana diya to kharab, kam bana diya to press khaali baithega. Dono galat.

Toh engine ko ek saath 5 cheezein balance karni padti hain:

Demand poora karo (fulfilment)

GT inventory 72 ghante ke andar consume ho jaaye (rule R5)

Mould / press / machine ki physical limit na toote (R3, capacity)

Changeover (mould change, size change) minimum ho - warna capacity waste

Lot size plant ke rules ke andar rahe (B12 floor: PCR 150, TBR 70)

## 1.2  Technical stack - aur kyun

| Choice | Kya use kiya | Kyun |
| --- | --- | --- |
| Language | Python 3.11 | Plant team maintain kar sakti hai; data libraries best hain |
| Data engine | Polars + DuckDB + Parquet | Pandas 4.4 GB MES data pe hang ho jaata hai. Polars 10-50x fast |
| Algorithm | Heuristic greedy + SA / Tabu / LNS | CP-SAT / MILP deliberately NAHI - measure karke fayda nahi mila |
| Learning | Classical statistics + pattern mining | ML / RL / LLM NAHI - plant ko explainable chahiye, black box nahi |
| Storage | Har layer sirf FILES se baat karti hai | Koi bhi single layer alag se re-run ho sakti hai; har number traceable |

Yeh deliberate design decisions hain, majboori nahi ML aur MILP dono try karke reject kiye gaye hain - measurement ke saath. L9 optimiser ko 300 second budget diya gaya tha: usne 1,428 candidates search kiye aur 0 moves accept kiye, nau ke nau cost tier wahin ke wahin rahe. Isliye hataya gaya. Yeh "hum kar nahi paaye" nahi hai - yeh "maapa, fayda nahi tha" hai.

## 1.3  Repository structure

| Folder | Kya rakha hai |
| --- | --- |
| INPUT/raw/ | Plant ke 18+ original workbooks / CSV / PDF - bilkul jaise mile the |
| INPUT/derived/ | 36 frozen mined masters (parquet) - engine inko seedha padhta hai |
| INPUT/cycletime/ | Build aur cure cycle-time workbooks |
| INPUT/opening_gt_manual/ | Plant ne manually count kiya hua GT floor stock |
| schedule/send/planner/cmbc/ | LIVE ENGINE - yahi chalta hai |
| schedule/send/warehouse/derived/ | MES history se mine kiye gaye month-wise masters |
| schedule/send/runs/<name>/ | Ek run ka poora output - har layer ka parquet + log |
| schedule/send/output/<pack>/ | Final BTP Excel pack jo plant ko jaata hai |

WARNING - teen engines hain, sirf EK zinda hai planner/cmbc/ = LIVE (yahi chalta hai). planner/engine/ = purana prototype. planner/plan/, learn/, kb/, optimize/ = RETIRED generation-1. Teen alag sessions galat codebase pe kaam kar chuke hain. Koi bhi scheduling change SIRF planner/cmbc/ mein hota hai.

# 2.  Architecture - Do Phases, L0 se L12 tak

## 2.1  Do phases

Poora engine do hisson mein bata hua hai:

| Phase | Layers | Sawal jiska jawab deta hai |
| --- | --- | --- |
| PHASE A | L0 - L4.5 | KYA banana hai aur KITNA banana hai? |
| PHASE B | L5 - L12 | KAHAN banana hai aur KAB banana hai? |

Phase A demand ko lekar usse "net requirement" aur "lots" mein badalta hai. Phase B un lots ko actual press aur machine pe, actual time slot pe baithata hai.

## 2.2  Poora layer map

| Layer | Naam | Kya karta hai | Output file |
| --- | --- | --- | --- |
| L0 | Learn (offline) | MES history se tau*, yields, press availability seekhta hai | warehouse/params/ |
| L1 | Preflight | Input gate - saare masters check, ERROR pe exit 1 | preflight_<M>.parquet |
| L2 | Capability (offline) | Kaunsa GT kaunsi machine / press / mould pe chal sakta hai | cap_machine / cap_press / cap_mould / cap_ttl_groups |
| L3 | Ceiling (offline) | Cavities nikalta hai + RCCP capacity report | l3_cavities.parquet |
| L4 | Net Requirement | Demand minus stock = kitna actually cure karna hai | net_requirement_<M> |
| L4.5 | Lot Sizing | Net requirement ko CURE lots mein tod-ta hai | l45_lots_<M> |
| - | Partition | Static GT -> machine map (month-stamped) | gt_machine_partition.parquet |
| L5 | Cure Campaign Master | PLAN YAHAN JANM LETA HAI - press pe campaign baithata hai | cure_campaigns.parquet |
| L7 | Pull Release | Building ko ULTA release karta hai (~4,000 lines - asli kaam) | build_schedule / gt_events / carry_forward_gt |
| L10 | Discretise | Time ko shift-grid pe todta hai, sequence banata hai | shift rows, mould_changes |
| L11 | Validate | 40 invariants check karta hai | l11_invariants.parquet |
| - | BTP Export | Plant format Excel pack banata hai | output/<pack>/ |

L6, L8, L9, L12 kahan gaye? Yeh RETIRED hain (planner/cmbc/_retired/). Verify kiya gaya - inko hataane se har plan artefact bit-identical rehta hai aur BTP pack ke saare 34 sheets match karte hain. Matlab inka output koi padh hi nahi raha tha.

## 2.3  Ek command mein poora mahina

main.py orchestrator hai. August 2026 ke liye ~30 second lagta hai:

cd schedule/send ./.venv/Scripts/python.exe main.py plan --month 2026-08 \ --run aug_ship --out output/AUG2026_pack \ --opening-gt opening_gt_manual_2026-08.parquet

Yeh andar se yeh steps chalata hai. Har step ka stdout runs/<name>/log_<step>.txt mein jaata hai:

| # | Step | Kya hota hai |
| --- | --- | --- |
| 00 | preflight | Input gate - allowable machine, PCR inch, TT/TL, press, mould, cycle time, opening GT, partition stamp |
| 00a | l2_ttl_b16 | TT/TL (tube-type / tubeless) groups aur B16 machine reach split |
| 01 | l4_net_requirement | Demand - stock = net cure requirement |
| 02 | l45_lotsize | Cure lots banata hai |
| 02b | l4b_capacity_flow | GT-level aur machine-level capacity flow check |
| 03 | partition | GT -> machine static map (agar month stamp galat hai to rebuild) |
| 04 | l5_cure_master | CURE CAMPAIGNS - plan ka janm |
| 05 | l7_pull_release | BUILD SCHEDULE - ulta release |
| 06 | l10_discretise | Shift grid + sequencing + mould changes |
| 07 | l11_validate_plan | 40 invariants |
| 08 | gt_sku_share | GT ko wapas SKU mein tod-na (BTP ke liye) |
| 09 | btp_export | Plant format Excel |
| 10 | shift_pack | 13-sheet detailed shift schedule |

# 3.  Inputs - Hum Kaunsi Files Use Karte Hain aur Kyun

Sabse zyada sawal yahin aate hain, isliye yeh section sabse detail mein hai. Inputs teen tarah ke hain:

| Type | Kahan se aata hai | Kitne | Kab badalta hai |
| --- | --- | --- | --- |
| Plant raw workbooks | Plant team email / share karti hai | 18+ | Jab plant naya master bheje |
| Frozen derived masters | Raw se ek baar mine karke freeze kiye | 36 (INPUT/derived/) | Rarely - jab raw badle |
| MES-mined month masters | 8 mahine ki MES history (32 M rows) | Month-wise | Har mahine rebuild |

## 3.1  Plant ke RAW workbooks (INPUT/raw/)

| File | Kya deta hai | Kis layer mein use hota hai |
| --- | --- | --- |
| August_Demand_PCR_TBR_Classification.xlsx | Mahine ka DEMAND - SKU wise, PCR/TBR classified | L4 (net requirement) - yahi sab kuch shuru karta hai |
| PCR BUILDING ALLOWABLE MATRIX.xlsx | Kaunsa GT kaunsi PCR TBM machine pe ALLOWED hai | L7 - hard constraint |
| TBR BUILDING ALLOWABLE MATRIX.xlsx | Wahi TBR ke liye (TBM 01 - TBM 09) | L7 - hard constraint |
| Recipemaster 1.xlsx + recipelookup 1.xlsx | SKU -> recipe -> GT ka chain | gt_sku_master banane mein |
| wcmaster 1.xlsx | Work centre master - press IDs, machine IDs | Press / machine naming |
| mould_inv_ctp_17072026.csv | MOULD INVENTORY - kaunsa mould kitne hain | L5 - R3 constraint (concurrency limit) |
| curing_item_mould_mapping 2.csv | GT -> mould mapping | cap_mould |
| Master_Mapping_Mould_SKU.csv | Mould -> SKU mapping | Cross-check |
| Master_Building_ChangeoverTime_pcr/tbr.csv | Building changeover time (same size vs diff size) | L7 sequencing cost |
| SKU_Construction_Clusters_PCR/TBR.xlsx | Construction cluster - kaunse SKU similar hain | Sister-SKU grouping, changeover saving |
| percentage weightage on tbmmachine....xlsx | 1 saal ka machine weightage per SKU | machine_weightage - preference order |
| ALL PCR CTP SKUS.xlsx | PCR ke saare CTP SKUs ki list | Scope define karta hai |
| CTP Set up building, curing and inspection.xlsx | Setup times | build_setup_catalogue |
| Ageing spec.pdf | GT ageing specification (72 h ka basis) | R5 rule ka source |

## 3.2  Frozen derived masters (INPUT/derived/) - 36 files

Yeh woh files hain jo raw se ek baar nikal kar FREEZE kar di gayi hain. Engine har run mein inko seedha padhta hai - dobara mine nahi karta. Isliye ek fresh clone bhi poora mahina replan kar sakta hai.

Sabse important 12:

| File | Kya hai | Kyun critical hai |
| --- | --- | --- |
| allowed_machine_matrix.parquet | Plant ka apna statement - GT x building machine | HARD constraint. PCR eligibility median 3 machines |
| allowed_press_matrix.parquet | GT x press eligibility (92 PCR / 79 TBR press) | Plant ka apna statement, mined se BROADER |
| gt_machine_partition.parquet | Static GT -> machine map, MONTH-STAMPED | Har mahine rebuild zaroori. Stale = July mein 0.58 pt loss |
| running_moulds_2026-08.parquet | ABHI press pe kaunsa mould laga hai | L5 warm start - pehla changeover bachata hai |
| opening_gt_inventory.parquet | Mahine ki shuruaat mein GT floor stock | L4 net requirement se ghatta hai |
| mould_cavity.parquet | Har mould mein kitni cavity | Cure rate calculation |
| press_mould_change.parquet | Per-press mould change time (PCR 210-430 min) | L5 press reservation - ise median lena bug tha |
| cycle_time_building.parquet | Per-machine seconds per tyre (PCR 49-78 s) | Build duration |
| cycle_time_curing.parquet | Per-press cure cycle + capacity per day | Cure duration |
| gt_size.parquet | GT ka rim / size | Same-size grouping, rim lock |
| tt_tl.parquet | Tube-Type vs Tubeless flag | B16 - TT aur TL mix nahi kar sakte |
| machine_rim_lock.parquet | Machine pe rim lock | Rim changeover mehnga hai |

Baaki 24: aging_limits, build_setup_catalogue, calendar_shifts, capacity_machine_day, capacity_press_day, gt_home_machine, gt_sister_group, gt_sku_master, lot_size, machine_gt_share, machine_weightage, pcr_inch_eligibility, prep_changeover, press_class_pcr, press_platen_master, semi_finished_ageing, sku_con_cluster, sku_construction, tbr_machine_certified, running_moulds_2026-07, gt_size.pre_rimfill, allowed_machine_matrix.bak, gt_machine_partition.provenance.json, MANIFEST.csv.

## 3.3  MES-mined month masters (warehouse/derived/)

Yeh 8 mahine (Dec 2025 - Jul 2026) ki MES history se nikale jaate hain - lagbhag 32 million rows, 4.4 GB CSV.

| File | Kya hai |
| --- | --- |
| net_requirement_<M>.parquet | L4 ka output - demand, usable stock, net_cure, gross_build |
| l45_lots_<M>.parquet | L4.5 ka output - lot count aur lot size per GT |
| cap_machine_<M> / cap_press_<M> | Mined eligibility - MES mein jo actually chala |
| cap_mould_<M> | Mould count + max_concurrent_presses (R3 ka basis) |
| cap_ttl_groups_<M> | TT/TL group split |
| l3_cavities.parquet | Per-press effective cavities aur cycle_s |
| b16_machine_reach_<M> | B16 gate - machine kaunse GT tak pahunch sakti hai |

Important nuance - do alag resolver hain input_derived() aur wh_derived() ALAG functions hain, jaan-boojh kar. 21 filenames dono jagah hain; bees byte-identical hain lekin press_mould_change.parquet ALAG hai. L5 aur L10 warehouse wali copy padhte hain. Dono ko merge karna cure schedule chupke se badal dega.

## 3.4  Month inputs kaise ingest karte hain

Jab plant nayi files bhejta hai, yeh do commands chalte hain:

# Demand $PY -m scripts.ingest_orderbook_demand \ --xlsx "../../INPUT/raw/August_Demand_PCR_TBR_Classification.xlsx" \ --sheet "August Demand Classified" --month 2026-08 # Opening GT (manual floor count) $PY -m scripts.ingest_manual_opening_gt --month 2026-08 --age-h 24 \ --pcr "../../INPUT/opening_gt_manual/gt_inventory_manual_pcr_20260801.xlsx" \ --tbr "../../INPUT/opening_gt_manual/gt_inventory_manual_tbr_20260801.xlsx"

# 4.  Poora Flow - Step By Step, Demand Se BTP Tak

Ab hum exactly wahi trace karenge jo aapne poocha: demand aata hai, PCR/TBR mein bat-ta hai, allowable check hota hai, phir planning aur curing.

## 4.1  STEP 1 - Demand aata hai aur PCR / TBR mein bat-ta hai

Plant ka demand workbook (August_Demand_PCR_TBR_Classification.xlsx) SKU-level demand deta hai, already PCR / TBR classified. Ingest script yeh karta hai:

SKU -> GT code translate karta hai (gt_sku_master ke through, curing-recipe chain se).

Plant column se PCR / TBR alag karta hai.

Same GT ke multiple SKU ko jod deta hai.

August 2026 ka result:

| Plant | GT codes | Demand (tyres) |
| --- | --- | --- |
| PCR | 73 | 4,29,146 |
| TBR | 37 | 99,019 |
| TOTAL | 110 | 5,28,165 |

GT NAMESPACE TRAP - yeh do baar debugging cost kar chuka hai Plant GT code ko kam se kam 4 alag shapes mein likhta hai. Engine sirf EK mein plan karta hai (v_build.itemCode). TBR BOM "GT 5001" likhta hai jabki TBR MES size-led likhta hai - dono namespaces mein ZERO string overlap hai. Isliye bridge hamesha SKU pe hota hai, GT code pe kabhi nahi. scripts/gt_namespace.py hi ekmatra bridge hai; ambiguity pe None return karta hai, guess nahi karta.

## 4.2  STEP 2 - Preflight (L1) : Input gate

Kuch bhi plan karne se pehle engine saare masters check karta hai. Yeh MES-free gate hai:

Allowable machine matrix present hai? Har demand GT cover hua?

PCR inch eligibility, TT/TL groups theek hain?

Press master, mould master, cycle time present hain?

Opening GT file mil rahi hai?

PARTITION KA MONTH STAMP SAHI HAI? - agar galat hai to BLOCKING ERROR, exit 1.

Output: preflight_<M>.parquet. Koi bhi ERROR mile to engine aage badhta hi nahi. Yeh jaan-boojh kar hai - galat master ke saath plan banane se accha hai plan hi na bane.

## 4.3  STEP 3 - L4 : Net Requirement (kitna cure karna hai)

Formula seedha hai:

net_cure = demand - usable_opening_stock gross_build = net_cure / cure_yield (yield loss adjust)

August 2026:

| Plant | Demand | Usable stock | From stock | Net cure | Gross build |
| --- | --- | --- | --- | --- | --- |
| PCR | 4,29,146 | 4,418 | 4,395 | 4,29,146 | 4,26,028 |
| TBR | 99,019 | 1,028 | 1,028 | 99,019 | 99,822 |

Dhyan dein: opening stock bahut kam hai (PCR 4,418 tyres = ~8 ghante ka production). Isliye mahine ki shuruaat mein koi cushion nahi hai - yeh START DIP ka ek bada karan hai (Section 8).

## 4.4  STEP 4 - L4.5 : Lot Sizing

Net requirement ko CURE lots mein tod-a jaata hai. Yaad rakhein - yeh CURE lot hai; build slices ka koi minimum nahi hota.

min_cure_lot = moulds x cavities x (campaign_min_h x 60 / cycle_min)

| Plant | GT count | Need | Lots bane | min_lot (p50) | B12 fixed floor |
| --- | --- | --- | --- | --- | --- |
| PCR | 73 | 4,26,028 | 389 | 202.8 | 150 |
| TBR | 37 | 99,822 | 221 | 70.0 | 70 |

B12 lot floor - TBR ka sabse bada issue TBR ka min_lot poore 37 GT pe 70 fixed hai. Jab kisi GT ka bacha hua requirement 70 se kam ho jaata hai, woh build nahi ho sakta - "would breach min_lot". TBR ke 6,330 unfed tyres mein se 6,100 (96 %) isi wajah se hain. Yeh ENGINEERING problem nahi hai - yeh PLANT RULING hai. Plant ko decide karna hai ki sub-floor lot allowed hai ya nahi.

## 4.5  STEP 5 - Allowable Check aur Partition

Yeh do alag cheezein hain, aksar confuse hoti hain:

|  | ALLOWABLE MATRIX | PARTITION |
| --- | --- | --- |
| Kya hai | Plant ka rule - GT x machine ALLOWED hai ya nahi | Engine ka decision - GT ko kaunsi machine par DAALNA hai |
| Source | Plant ka workbook | CP-SAT solver, demand + capacity se |
| Nature | HARD constraint (haan / naa) | Assignment / preference |
| Validity | Jab tak plant na badle | SIRF ek mahine ke liye - month-stamped |

Allowable check ka semantics:

Agar (plant, GT) matrix mein hai -> SIRF listed machines allowed. Baaki sab drop.

Agar (plant, GT) matrix mein NAHI hai -> mined eligibility as-is chalti hai (taaki naya GT unplannable na ho).

Partition har mahine rebuild karna ZAROORI hai Partition ek mahine ki demand aur calendar hours ke hisaab se banta hai. L7 doosre mahine ke stamp wale partition pe plan karne se INKAAR kar deta hai. July mein stale partition use hua tha - 0.58 pt fulfilment aur 10.3 pt same-size ka nuksaan hua, aur SAARE gates paas ho gaye the. Isliye ab blocking ERROR hai.

## 4.6  STEP 6 - L5 : Cure Campaign Master (PLAN KA JANM)

Yeh sabse important layer hai. Yahan actual plan banta hai.

L5 kya karta hai:

Saare cure lots ko ek queue mein daalta hai, BADE se CHHOTE ke order mein (scarcity priority).

Har lot ke liye eligible press dhundta hai (cap_press + allowed_press_matrix).

Jo press sabse pehle free ho raha hai use uthata hai.

R3 check - ek GT ke liye ek saath chalne wale press uske mould count se zyada nahi ho sakte.

Mould change time reserve karta hai (per-press, PCR mein 210-430 min).

Campaign ka start_ts aur end_ts fix kar deta hai.

Ek CRITICAL baat - RELEASE FLOOR:

PCR release floor = tau* + build_band = 4.319 h + 7.54 h = 11.86 ghante TBR release floor = 4.809 h + 5.37 h = ~10.18 ghante

Matlab: t0 (1 August 07:00) pe koi bhi press turant start nahi kar sakta. Har press ko kam se kam 11.86 ghante (PCR) intezaar karna padta hai. Kyun? Kyunki building ko pehle GT banana hai. Yeh START DIP ka doosra bada karan hai.

August 2026 L5 output:

| Plant | Campaigns | Qty | Press hours | Press use |
| --- | --- | --- | --- | --- |
| PCR | 280 | 4,12,897 | 65,677 | 86 |
| TBR | 191 | 98,625 | 58,989 | 79 |

## 4.7  STEP 7 - L7 : Pull Release of Building (~4,000 lines)

Ab building ko ULTA release kiya jaata hai. Har cure campaign ke liye:

build_start = cure_start - tau* - build_duration

L7 ka kaam:

Har campaign ke liye eligible building machine dhundna (allowable matrix ke andar).

Machine par slot dhundna - agar busy hai to aage-peeche adjust karna.

B16 gate - TT aur TL ko mix na hone dena.

Changeover cost minimise karna - same size / sister SKU ko saath rakhna.

GT ledger maintain karna - har tyre ka +1 (build) aur -1 (cure).

Jo feed nahi ho paaya use build_starved.parquet mein likhna.

August 2026 L7 output:

| Plant | Build rows | Built qty | Machines | Utilisation | Starved |
| --- | --- | --- | --- | --- | --- |
| PCR | 2,635 | 4,08,950 | 11 | 83.5 % | 2,066 |
| TBR | 3,676 | 97,985 | 9 | 81.7 % | 27 |

Building LATE nahi hai - yeh maapa gaya hai Build se cure tak ka wait: PCR p50 = 4.3 ghante, TBR p50 = 4.7 ghante. Maximum 71.6 h / 68.6 h - 72 ghante ki limit kabhi nahi tooti. Sirf 0.5 % PCR tyres "no feasible release" hote hain. Jo press late start karte hain unme se sirf 4 (PCR) aur 7 (TBR) building ka intezaar kar rahe the - baaki 68 PCR aur 62 TBR presses ke liye GT PEHLE SE FLOOR PE TAIYAR THA.

## 4.8  STEP 8 - L10 : Discretise aur Sequence

Continuous time ko plant ke shift grid pe map kiya jaata hai:

Plant day 07:00 se 07:00 chalta hai (wall-clock midnight nahi).

Shift A = 07-15, Shift B = 15-23, Shift C = 23-07.

Export mein "date" PLANT-DAY date hai, wall-clock date nahi. C shift ko wall clock se label karne pe ek baar 28.7 % build rows galat label ho gayi thi.

Mould changes explicitly list hote hain (mould_changes.parquet).

## 4.9  STEP 9 - L11 : Validation (40 invariants)

Plan ko 40 alag rules pe check kiya jaata hai. Kuch examples:

Koi machine ek waqt mein do lot nahi chala rahi (overlap check).

Koi mould double-book nahi hua.

GT ledger kabhi negative nahi gaya (starvation check).

R5 - koi GT 72 ghante se zyada nahi baitha.

G8 - GT WIP rail (PCR 4,800 / TBR 1,400) ke andar hai.

Same-size share threshold ke upar hai.

Sub-floor run share plant ke apne share se zyada nahi hai.

## 4.10  STEP 10 - BTP Export aur Verify

Aakhir mein plant format Excel banta hai, aur ek INDEPENDENT verifier chalta hai:

$PY scripts/export_shift_schedule.py aug_ship 2026-08 output/AUG2026_pack $PY scripts/verify_export.py output/AUG2026_pack 2026-08

Verifier planner ko import NAHI karta - jaan-boojh kar verify_export.py aur validate/violations.py har check ko exported files se DOBARA derive karte hain. Agar verifier planner ke andar ke functions call karega to woh sirf yeh prove karega ki planner apne aap se sehmat hai. Yeh independence deliberate hai.

# 5.  Business Rules Jo Plan Ko Control Karte Hain

Total 46 numbered rules hain (BUSINESS_RULES.md mein, B/P/C/S/G/E prefixes ke saath). Jo sabse zyada asar daalte hain:

| Rule | Kya kehta hai | Value | Asar |
| --- | --- | --- | --- |
| R3 | Ek GT ke concurrent presses <= uske mould count | Per GT | Bade GT ki parallel capacity limit karta hai |
| R5 | GT shelf life | 72 ghante | Jaldi banane se rok-ta hai. NOT env-overridable |
| B12 | Build lot floor | PCR 150 / TBR 70 | Chhote residual build nahi ho paate |
| G8 | GT WIP rail | PCR 4,800 / TBR 1,400 | Zyada GT jama nahi hone deta |
| B16 | TT / TL separation | Group-wise | Tube-type aur tubeless mix nahi |
| B7 | Daily build quota | REJECTED | Try kiya, plant se better CV mila, isliye nahi lagaya |

Caps sirf ek jagah hain - config.py "Add a cap in config.py or nowhere." L7 aur L11 dono wahin se padhte hain, koi apni copy nahi rakhta. Ek baar duplicate value bug ban gaya tha: L7 1,400 enforce kar raha tha aur L11 1,500 pe grade kar raha tha.

## 5.1  Key learned parameters (L0 se)

| Parameter | PCR | TBR | Matlab |
| --- | --- | --- | --- |
| tau* (coupling buffer) | 4.319 h | 4.809 h | Build se cure tak ka MEDIAN gap |
| tau_min | 0.268 h | 0.268 h | Physically sabse kam gap |
| build_band (p50) | 7.54 h | ~5.37 h | Median campaign length |
| Press availability | 0.8897 | 0.8282 | MTBF/MTTR se nikala |
| Mould change time | 210-430 min (med 360) | 361 min (flat) | Per press |

SABSE BADI SEEKH - "A mined statistic is not a constraint" tau* aur min_lot dono plant ke MEDIAN the, aur dono ko HARD FLOOR bana diya gaya tha. Dono ne milkar 13.4 POINTS ka fulfilment loss kiya. Median ka matlab hai ki 50 % reality already usse behtar hai. Pehchaan: agar p01, p05, p10 sab ek jaise dikhein - to samajh jaao deewar banayi gayi hai, distribution nahi hai.

# 6.  August 2026 - Actual Results

## 6.1  Volume waterfall

| Stage | PCR | TBR | Kya hua yahan |
| --- | --- | --- | --- |
| Demand | 4,29,146 | 99,019 | Plant ka order book |
| Net cure requirement (L4) | 4,29,146 | 99,019 | Opening stock bahut kam tha |
| Cure campaigns placed (L5) | 4,12,897 | 98,625 | Press capacity full - 16,249 / 394 place nahi hua |
| BUILT (L7) | 4,08,950 | 97,985 | 2,066 / 27 starved |
| Fed in-month | 3,84,464 | 92,983 | Baaki month ke baad cure hua (tail) |
| Carry out to Sept | ~24,486 | ~5,002 | Yeh output hai, loss nahi |

## 6.2  Capacity picture - kaun bottleneck hai

| Resource | PCR | TBR |
| --- | --- | --- |
| Building machines | 11 | 9 |
| Build capacity (nameplate) | 5,02,839 (117 % of demand) | 1,17,572 (119 %) |
| Build utilisation | 83.5 % | 81.7 % |
| Build idle capacity | 86,352 tyres | 21,686 tyres |
| Presses used | 86 | 79 |
| Cure ceiling (as modelled) | 4,07,396 (95 % of demand) | 1,06,415 (107 %) |
| Press utilisation | 102.6 % (month se bahar) | 100.4 % |

Nateeja saaf hai PCR: cure ceiling 4,07,396 hai aur demand 4,29,146 - matlab scheduling shuru hone se PEHLE hi hum 5 % short hain. Building ke paas 86,352 tyres ki khaali capacity hai lekin usse koi fayda nahi kyunki curing hi nahi le paa rahi. TBR: cure ceiling 107 % hai - TBR capacity-bound NAHI hai. TBR ka issue lot floor (B12) hai.

## 6.3  Per-machine building load (PCR) - imbalance

Yeh ek real problem hai jo abhi bottleneck nahi hai, lekin curing theek hote hi ban jaayegi:

| Machine | sec/tyre | Capacity/month | Built | Utilisation | Idle capacity |
| --- | --- | --- | --- | --- | --- |
| TBMPCR5 | 49 (sabse fast) | 54,661 | 27,686 | 52.9 % | 25,741 |
| TBMPCR7 | 49 (sabse fast) | 54,661 | 40,555 | 75.8 % | 13,222 |
| TBMPCR4 | 49 | 54,661 | 45,535 | 91.9 % | 4,423 |
| TBMPCR10 | 51 | 52,518 | 51,544 | 94.0 % | 3,157 |
| TBMPCR8 | 66 | 40,582 | 37,589 | 94.5 % | 2,236 |
| TBMPCR11 | 69 (dheema) | 38,817 | 34,692 | 97.0 % | 1,151 |
| TBMPCR9 | 78 (sabse dheema) | 34,338 | 31,866 | 86.9 % | 4,503 |

Dhyan dein: sabse TEZ machine (TBMPCR5, 49 s/tyre) sirf 52.9 % chal rahi hai, jabki sabse DHEEMI machines 87-97 % pe hain. Kyun? Kyunki building cure campaign se ulta release hota hai - machine ki speed ke hisaab se nahi chunta, jo campaign feed karna hai uske hisaab se chunta hai.

# 7.  START DIP aur END DIP - Poora Explanation

Yeh sawal sabse zyada poocha jaata hai, isliye poora hisaab yahan hai.

## 7.1  Pehle data dekho - daily cure volume

| Din | Cure PCR | Cure TBR | Press util PCR | Press util TBR | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | 4,386 | 1,085 | 33.0 % | 34.1 % | START DIP - bada |
| 2 | 10,352 | 2,372 | 77.0 % | 74.7 % | START DIP - recover |
| 3 | 12,709 | 3,028 | 95.6 % | 95.6 % | Almost normal |
| 4 | 13,276 | 3,082 | 99.7 % | 97.4 % | NORMAL |
| 5 - 15 | ~13,300 | ~3,085 | ~100 % | ~97.5 % | STEADY STATE |
| 16 - 28 | ~12,500 | ~3,120 | ~98 % | ~98 % | Steady, halka neeche |
| 29 | 12,566 | 3,071 | 97.0 % | 96.7 % | END DIP shuru |
| 30 | 11,960 | 3,051 | 94.3 % | 96.2 % | END DIP |
| 31 | 11,583 | 2,912 | 92.4 % | 92.0 % | END DIP - sabse neeche |

## 7.2  START DIP - 3 karan, teeno milke

KARAN 1 : Cold start - koi carry-in nahi (sabse bada)

Mahine ki shuruaat mein engine maanta hai ki kuch bhi chal nahi raha. Real plant mein 31 July raat ko machines chal rahi hoti hain aur 1 August subah bhi chalti rehti hain. Humara plan t0 (1 Aug 07:00) pe SAB KUCH ZERO se shuru karta hai. Isse pehle 12-24 ghante ka production window kho jaata hai.

KARAN 2 : Release floor ki deewar - 11.86 ghante (PCR)

L5 har press ko tau* + build_band = 11.86 ghante tak rok deta hai. Logic yeh hai ki building ko pehle GT banana hai. Lekin dono terms MEDIAN hain - tau* plant ka median coupling buffer hai (47 % tyres isse jaldi cure hote hain) aur build_band median campaign LENGTH hai, pehla lot banane ka time nahi. Physically pehla legal lot 2.35 ghante (PCR) mein ban sakta hai, 11.86 nahi.

KARAN 3 : Opening GT stock bahut kam

PCR ke paas sirf 4,418 usable GT tha (~8 ghante ka cure), TBR ke paas 1,028. Agar opening stock zyada hota to press turant start kar sakte the aur building ko catch-up ka time mil jaata.

Aur yahan asli baat - building LATE nahi thi Din 1 pe 86 mein se sirf 4 PCR press aur 79 mein se 7 TBR press building ka intezaar kar rahe the. Baaki 68 PCR press (1,888 ghante) aur 62 TBR press (2,368 ghante) is liye khaali the ki GT PEHLE SE TAIYAR THA, lekin L5 ne unka start time pehle hi 11.86 ghante pe fix kar diya tha. Udaharan: GT 1513 XPC1 MSIL 2.2 ghante mein ban gaya tha, uske 11 press 24.4 ghante pe start hue - 244 press-ghante barbaad. Press ne GHADI ka intezaar kiya, STOCK ka nahi.

## 7.3  END DIP - 3 karan

KARAN 1 : Horizon boundary

Jo campaign 31 August ke baad tak jaayegi woh "in-month" count nahi hoti. L5 aise campaign seat karne se katrata hai, isliye aakhri dino mein naya kaam kam milta hai. 56 campaigns 1 September ki line cross karte hain, 27,118 tyres lekar.

KARAN 2 : L4.5 ne quantity pehle hi freeze kar di

Lot quantities L4.5 mein fix ho jaati hain, press seat hone se PEHLE. Isliye jab mahine ke ant mein koi press free hota hai, koi campaign BADH kar use absorb nahi kar sakti. Plant yeh karta hai - hum nahi kar paate.

KARAN 3 : Hum front-load karte hain, plant back-load karta hai

GT 1513 (PCR ka sabse bada GT, 55,663 tyres, 35 moulds, 44 eligible press) pe maapa gaya:

|  | Din 1-22 | Din 23-31 | Pattern |
| --- | --- | --- | --- |
| Plant | 33,415 | 22,248 | 2,472/din - din 23 pe 60 % RAMP karta hai |
| Hamara plan | 38,998 | 15,103 | 1,678/din - dheere dheere GIR-ta hai |

Plant apne bade, zyada-mould wale GT ko ABSORBER ki tarah use karta hai. Jaise jaise chhote GT khatam hote hain aur press free hote hain, plant unhe GT 1513 pe re-tool kar deta hai - kyunki us GT ke paas mould headroom hai. Isliye plant ke paas month-end idle nahi hota, humare paas aakhri 5 dino mein 1,085 press-ghante idle hote hain.

## 7.4  Dip ka poora hisaab - aur yeh kyun important hai

Steady state daily rate lekar dip ka loss nikalte hain:

| Dip | PCR loss (tyres) | TBR loss (tyres) | Calculation |
| --- | --- | --- | --- |
| Din 1 | 8,931 | 2,000 | Steady 13,317 minus actual 4,386 |
| Din 2 | 2,965 | 713 | 13,317 minus 10,352 |
| Din 3 | 608 | 57 | 13,317 minus 12,709 |
| START DIP TOTAL | 12,504 | 2,770 |  |
| Din 29 | 751 | 69 | ~13,317 minus 12,566 |
| Din 30 | 1,357 | 89 |  |
| Din 31 | 1,734 | 228 |  |
| END DIP TOTAL | 3,842 | 386 |  |
| GRAND TOTAL DIP | 16,346 | 3,156 |  |

YEH SABSE BADA INSIGHT HAI PCR ka total gap (demand 4,29,146 minus campaigns 4,12,897) = 16,249 tyres. Dip ka total loss = 16,346 tyres. Yeh lagbhag EXACTLY BARABAR hai. Matlab: PCR ka poora shortfall sirf START DIP aur END DIP hai. Beech ke 25 din mein press 98-100 % pe chal rahe hain - wahan koi problem nahi hai. Agar sirf dono dip theek kar lein to PCR demand lagbhag poora ho jaayega.

## 7.5  Dip theek karne ke liye kya kiya ja sakta hai

| Solution | Kya karna hai | Kitna faida | Kaun decide karega |
| --- | --- | --- | --- |
| Warm start / carry-in | 31 July raat ka running state input mein lena | Din 1 ka bada hissa | PLANT RULING - ~4 h carry-in question |
| Release floor theek karna | tau* + band ki jagah per-GT actual build time | ~1,090 PCR + 1,496 TBR press-ghante | ENGINEERING (l56_loop) |
| Opening GT badhana | Mahine ke ant mein thoda zyada GT chhodna | Din 1 cushion | PLANT RULING |
| Phased order book | Demand mein weekly due dates maangna | Flat curve theek hoga, end dip kam | PLANT - data dena hoga |
| Back-loading (absorber) | Bade mould-rich GT ko month-end ke liye rakhna | End dip | ENGINEERING (PLANNER_L5_BACKLOAD) |
| Press roster theek karna | PCR press 17-22 wapas laana | ~24,552 tyres ka ceiling | PLANT RULING - decommissioned hain ya nahi? |

Ek important warning Demand mein phasing NAHI hai - August ke saare 5,28,165 tyres ek hi date (din 31) pe hain. Isliye engine ke paas koi deadline nahi hai, woh sirf size ke hisaab se sort karta hai aur earliest-feasible pe daal deta hai. Isse ek FLAT curve banti hai. Agar plant weekly due dates de de to yeh apne aap theek ho sakta hai - code mein flag pehle se hai (PLANNER_L5_EDD), bas data nahi hai.

# 8.  Known Gaps - Kya Abhi Theek Nahi Hai

Yeh section jaan-boojh kar honest hai. Har issue ke saath yeh bhi likha hai ki woh ENGINEERING task hai ya PLANT RULING.

## 8.1  Priority order mein

| # | Issue | Impact | Type |
| --- | --- | --- | --- |
| 1 | PCR press 17-22 (6 press) planner ko dikhte hi nahi | ~24,552 tyres/month ka cure ceiling | PLANT RULING |
| 2 | Demand mein phasing nahi (sab din 31 pe) | Flat curve, end dip | PLANT - data |
| 3 | Release floor median-based hai (11.86 h) | ~2,586 press-ghante = ~9,400 tyres | ENGINEERING |
| 4 | TBR B12 lot floor | 6,100 of 6,330 unfed TBR tyres | PLANT RULING |
| 5 | Cure capacity achieved-history se model hoti hai | Ceiling 95 % vs plant workbook 106 % | ENGINEERING + PLANT |
| 6 | Building machine imbalance (TBMPCR5 52.9 %) | Abhi bottleneck nahi, baad mein banega | ENGINEERING |
| 7 | gt_size rim coverage - 28 GT ka rim missing | Rim grouping kamzor | PLANT - data |
| 8 | Carry-in / horizon boundary question | +1.0 to 1.8 pt per plant | PLANT RULING |

## 8.2  Issue 1 detail - 6 press gayab kaise hain

masters/press_list_<month>.json ek hand-maintained file hai. Uska press count ghat raha hai:

| Month | PCR presses | Press 17-22 hain? |
| --- | --- | --- |
| 2026-05 | 91 | Haan - 20, 21, 22 |
| 2026-06 | 89 | Sirf 21, 22 |
| 2026-07 | 86 | NAHI |
| 2026-08 | 86 | NAHI |

Lekin yeh press REAL hain: MES mein 138-142 tyres/day cure kar rahe the, aur plant ka apna allowed_press_matrix inko "direct" mark karta hai 5 GT ke liye jinka August demand 35,332 tyres hai. GT 1772 NEO (1,178 tyres) ka plan ZERO ban jaata hai kyunki press 22 uska ekmatra allowed press hai.

Is file ka koi generator nahi hai press_list_<month>.json ko koi script nahi banati, uski koi provenance line nahi hai, aur woh kisi bhi defect ledger mein nahi hai. Ek hand-edited JSON chupke se plant ki cure ceiling set kar rahi hai. Plant se poochna hai: kya 17-22 decommission ho gaye, ya sirf mining window mein idle the?

## 8.3  Deliberate non-goals - inhe "fix" nahi karna hai

ML / RL / LLM nahi - plant ko explainable chahiye.

CP-SAT / MILP nahi - try karke measure kiya, fayda nahi mila.

Daily build quota (B7) REJECTED - humara interior CV plant se already behtar hai.

GT inventory G8 band ke NEECHE rehna INTENTIONAL hai - GT target nahi hai, buffer hai.

Curing ka cycleStart ulta naam hai (press-open = cycle END) - yeh source data ki galti hai, isse "theek" nahi karna.

Mould per (plant, GT, press) hain - ek primary mould per GT karne se 4.16 lakh phantom violations aaye the.

# 9.  Manager Q&A - Jo Sawal Aa Sakte Hain

## 9.1  Basic / Strategy

Q: Simple bhasha mein CTP Planner karta kya hai?

A: Demand leta hai aur poore mahine ka Building + Curing schedule banata hai - kaunsi machine par kya, kaunse press par kya, kis shift mein, kis order mein. Output Excel BTP pack hai jo plant seedha use karta hai.

Sabse badi baat: yeh dono stages ko SYNCHRONIZE karta hai. Building akela plan karna aasan hai, curing akela plan karna aasan hai - dono ko 72 ghante ki GT window ke andar match karana mushkil hai. Wahi yeh karta hai.

Q: Isse manually planning se kya fayda hai?

A: Teen cheezein: (1) 30 second mein poora mahina - manually 2-3 din lagte hain. (2) Har decision traceable hai - har number kisi parquet file se aata hai, koi guess nahi. (3) 40 automatic validation checks - overlap, double-booking, R5 breach, WIP rail - insaan se yeh miss ho jaate hain.

Q: Aap ML ya AI kyun use nahi kar rahe?

A: Deliberate decision hai. Plant ko explainable plan chahiye - agar press 187 pe GT 1513 gaya to kyun gaya, iska seedha jawab chahiye. ML black box deta hai.

Doosra, humare paas 8 mahine ka data hai - ML ke liye kam hai, statistics ke liye kaafi hai. Teesra, MILP/CP-SAT try kiya - L9 optimiser ne 300 second mein 1,428 options dekhe aur ek bhi accept nahi kiya. Isliye hataya. Yeh "kar nahi paaye" nahi hai, "maapa aur fayda nahi mila" hai.

## 9.2  Capacity aur Bottleneck

Q: Hum 4 lakh PCR aur 1 lakh TBR kyun nahi bana paa rahe?

A: Actually PCR mein hum 4,08,950 bana RAHE hain - 4 lakh se zyada. TBR mein 97,985 - thoda kam.

Jo poora nahi ho raha woh DEMAND hai: PCR 4,29,146 aur TBR 99,019. PCR mein cure ceiling hi 4,07,396 hai (demand ka 95 %) - matlab scheduling shuru hone se pehle hi hum 5 % short hain.

TBR alag case hai - uska cure ceiling 1,06,415 (107 %) hai, capacity ki problem NAHI hai. TBR ka issue B12 lot floor hai.

Q: Building bottleneck hai ya curing?

A: Saaf taur pe CURING. Building ke paas PCR mein 17 % aur TBR mein 18 % capacity khaali padi hai - 86,352 aur 21,686 tyres ke barabar. Press 100-102 % pe chal rahe hain.

Isliye building ko aur tez chalane se koi fayda nahi hoga - GT banega lekin press usko le nahi paayega, aur 72 ghante mein woh kharab ho jaayega.

Q: Toh building utilisation 83 % kyun hai? Use 95 % nahi hona chahiye?

A: Nahi - aur yeh important hai. Building PULL-RELEASED hai. Woh utna hi banata hai jitna curing le sakti hai. Agar hum use 95 % pe chala dein to extra GT banega jiske liye koi press nahi hai.

Build se cure ka wait already p99 pe 42 ghante (PCR) hai, aur limit 72 ghante hai. Zyada jaldi banane se tyres R5 breach ki taraf jaayenge. Building utilisation tabhi badhana chahiye jab cure capacity pehle badhe.

Q: Agar hum aur press laga dein to problem solve ho jaayegi?

A: Partly. Sabse pehle to 6 press jo PEHLE SE HAIN woh planner ko dikhte hi nahi (PCR 17-22). Woh ~24,552 tyres/month ka ceiling hai - naya kuch kharidna nahi padega.

Lekin dhyan rakhna hoga: ek baar test kiya gaya tha (PLANNER_PRESS_FROM_MATRIX=1) aur BUILT actually GIR gaya (-2,432 August mein) kyunki zyada press seats ka matlab hai zyada parallel campaigns, jisse building ko ek saath zyada GT feed karne padte hain aur changeover badh jaate hain. Toh press ke saath campaign coherence bhi theek karni hogi.

## 9.3  Dip ke sawal

Q: Mahine ke shuru mein production kam kyun hai?

A: Teen karan, teeno milkar: (1) Cold start - plan maanta hai ki 1 August 07:00 pe kuch chal nahi raha, jabki asal mein plant chal raha hota hai. (2) Release floor - L5 har press ko 11.86 ghante rok deta hai taaki building pehle GT bana le. (3) Opening GT stock bahut kam hai - PCR mein sirf 4,418 tyres.

Numbers: Din 1 pe PCR ne 4,386 tyres cure kiye jabki steady rate 13,317 hai - 33 % pe. Din 3 tak 95 % ho jaata hai.

Q: Kya yeh building ki galti hai? Building time pe GT nahi de raha?

A: NAHI. Yeh humne alag se maapa hai. Din 1 pe 86 mein se sirf 4 PCR press building ka intezaar kar rahe the. Baaki 68 press khaali the jabki unka GT PEHLE SE FLOOR PE TAIYAR THA.

Sabse saaf example: GT 1513 XPC1 MSIL 2.2 ghante mein ban gaya tha, lekin uske 11 press 24.4 ghante pe start hue. 244 press-ghante barbaad. Press ne GHADI ka intezaar kiya, STOCK ka nahi. Yeh L5 ka release floor ka issue hai, building ka nahi.

Q: Mahine ke ant mein dip kyun aata hai?

A: Teen karan: (1) Horizon - jo campaign 31 August ke baad jaayegi woh in-month count nahi hoti, isliye L5 use seat karne se katrata hai. (2) L4.5 quantities pehle freeze kar deta hai, isliye koi campaign BADH kar free press ko absorb nahi kar sakti. (3) Plant back-load karta hai, hum front-load karte hain.

Plant apne bade mould-rich GT ko ABSORBER ki tarah use karta hai - din 23 pe GT 1513 ko 60 % ramp kar deta hai. Hum ulta decay karte hain. Isliye plant ke paas month-end idle nahi hota, humare paas aakhri 5 dino mein 1,085 press-ghante idle hote hain.

Q: Dip ka total nuksaan kitna hai?

A: PCR: start dip 12,504 + end dip 3,842 = 16,346 tyres. TBR: 2,770 + 386 = 3,156 tyres.

Aur yeh sabse important baat hai - PCR ka TOTAL gap 16,249 tyres hai. Dip ka loss 16,346 hai. Ye lagbhag exactly barabar hai. Matlab PCR ka poora shortfall sirf do dip hain. Beech ke 25 din mein press 98-100 % pe chal rahe hain, wahan koi problem nahi hai.

Q: Dip theek karne mein kitna time lagega?

A: Alag-alag hai. Sabse sasta: plant se weekly due dates maang lein - code mein flag pehle se hai, sirf data chahiye. Press roster ka sawal bhi plant se ek email ka kaam hai.

Engineering side pe l56_loop naam ka module PEHLE SE LIKHA HUA hai jo yeh exact problem solve karta hai - L5 aur L7 ko baat karwata hai. Woh abhi pipeline mein wired nahi hai. Use test karne mein ~5 minute lagenge.

## 9.4  Data aur Trust

Q: Yeh numbers kahan se aa rahe hain? Bharosa kaise karein?

A: Har number ek parquet file se aata hai jo run directory mein padi hai. Koi in-memory calculation nahi hai - har layer sirf files se baat karti hai. Aap khud kholkar dekh sakte hain.

Uske upar ek INDEPENDENT verifier hai (verify_export.py) jo planner ka koi function call nahi karta - woh sirf exported CSV padhkar har check dobara derive karta hai. Agar verifier planner ke andar jhaankta to woh sirf yeh prove karta ki planner apne aap se sehmat hai.

Q: Agar koi master file galat ho to kya hoga?

A: Preflight (L1) pehle hi rok dega - ERROR pe exit 1, plan banega hi nahi. Partition ka month stamp galat ho to blocking ERROR aata hai.

Lekin honest rehna zaroori hai: ek gate SIRF violations check kar sakta hai, OMISSIONS nahi. Press roster ka issue isi wajah se itne mahine chhupa raha - gate "0 violations, clean" bol raha tha jabki 6 press file se hi gayab the.

Q: Kya yeh plan real plant mein chal sakta hai?

A: Haan - August 2026 ka pack 34 sheets ke saath generate hua hai aur ek fresh clone se bit-identical reproduce hota hai. L11 ke 40 invariants pass hote hain (overlap, double-booking, negative GT, R5).

Ek honest disclaimer: BTP mein kuch building machine codes abhi unresolved hain (machine_code_map_UNRESOLVED.csv). Unko guess karna khatarnak hoga - building machine ka output inspection station pe chala jaayega. Woh plant se confirm karna hai.

## 9.5  Process aur Governance

Q: Koi change karne se pehle kya process hai?

A: Har change ko A/B measure karna zaroori hai, do mahine (July + August) aur do plant (PCR + TBR) pe. Agar sign mixed hai to change reject hota hai.

Grading BUILT pe hoti hai, in-month pe nahi - kyunki in-month tail-sensitive hai aur cure jaldi kheenchne se badh jaata hai bina koi tyre bane. Yeh humne seekha hai: ek change +3.4 pt dikha raha tha jabki actually 2,432 tyres KAM bane the.

Q: Ab tak kitne changes try kiye aur kitne kaam aaye?

A: SESSION_LOG mein poora record hai: 9 scheduler changes mein se 8 NEGATIVE measure hue. Har jeet ek DATA fix thi, scheduling logic ki nahi.

Yeh humara sabse important learning hai - is engine mein algorithm badalne se aam taur pe nuksaan hota hai, aur master data theek karne se faida hota hai. Isliye priority list mein data fixes upar hain.

Q: Documentation kahan hai?

A: Paanch documents hain, padhne ka order bhi fix hai: PARTITION_AND_CHANGEOVER.md (defect ledger - pehle yeh), EXPERT_AUDIT.md (independent audit), MEMORY.md (engineering log), SESSION_LOG (har test uske deciding number ke saath), BUSINESS_RULES.md (46 rules with status).

Khaas baat yeh hai ki yeh project apni GALTIYAN likhta hai, us measurement ke saath jisne use pakda. Rejected experiments code mein hi rehte hain, gated off, apne number ke saath - taaki koi dobara blindly na chalaye.

Q: Agar main ek hi cheez approve karun to kaunsi?

A: Plant se do sawal ka jawab: (1) PCR press 17-22 decommissioned hain ya nahi? (2) Kya demand workbook mein weekly due dates mil sakti hain?

Dono ke liye humein koi code nahi likhna. Pehla ~24,552 tyres/month ka ceiling wapas laata hai, doosra flat concurrency curve theek karta hai jo end dip ki jad hai. Dono milkar dono dip pe attack karte hain.

# 10.  Glossary - Terms Ki List

| Term | Full form / Matlab |
| --- | --- |
| GT | Green Tyre - kachcha tyre, building ke baad curing se pehle. 72 ghante shelf life |
| PCR | Passenger Car Radial - chhoti gaadi ke tyre |
| TBR | Truck Bus Radial - bade vehicle ke tyre |
| TBM | Tyre Building Machine |
| Press | Curing press - jahan GT pakta hai |
| Mould | Saancha - press ke andar lagta hai. Per (plant, GT, press) hota hai |
| Cavity | Ek press mein ek saath kitne tyre - PCR ~3.4 effective, TBR ~2.4 |
| tau* (tau star) | Build se cure tak ka median gap. PCR 4.319 h, TBR 4.809 h |
| Campaign | Ek press par ek GT ka continuous run |
| Lot | Ek batch. Cure lot ka floor hota hai, build slice ka nahi |
| Changeover | Machine / press ko doosre GT ke liye badalna - time lagta hai |
| Same-size share | Kitna production same size ke saath-saath hua - zyada = kam changeover |
| BUILT | Is mahine actually banaye gaye tyres (OPENING_STOCK ko chhod kar) |
| Fed | Press mein daale gaye tyres - isme opening stock bhi shaamil hai |
| Cured in-month | Fulfilment ka numerator = built + opening - closing |
| Carry-out / tail | Jo campaign mahine ke baad tak chalti hai - yeh output hai, loss nahi |
| BTP | Plant ka target Excel format jisme final schedule jaata hai |
| MES | Manufacturing Execution System - plant ka actual production data |
| Invariant | Aisa rule jo hamesha sach hona chahiye - L11 mein 40 hain |
| R3 | Concurrent presses <= mould count |
| R5 | GT shelf life 72 ghante |
| B12 | Build lot floor - PCR 150, TBR 70 |
| G8 | GT WIP rail - PCR 4,800, TBR 1,400 |
| B16 | Tube-Type aur Tubeless alag rakhna |

--- Document End ---

Saare numbers runs/FINAL_aug (month 2026-08) ke actual artefacts se nikale gaye hain. Koi bhi number dobara verify kiya ja sakta hai.