# July 2026 — Plant vs Engine

Where every missing tyre goes, why, and what would recover it

Run runs/jul_v13 (V13) · unpartitioned · generated from l11_invariants.parquet, gt_events.parquet, build_schedule.parquet, cure_campaigns.parquet, build_starved.parquet and net_requirement_2026-07. Reproduce with:  PYTHONPATH=. python scripts/diag_plant_vs_engine.py jul_v13 2026-07

# 0. Why July, and the one caveat that governs this whole report

July's demand IS the plant's own July production, taken from MES. For every GT, plant production = demand, and the plant therefore scored 100 % by construction. That makes July the only month where a per-GT plant-vs-engine comparison is fair rather than a comparison against a forecast.

It also makes July the easy month, and the flattering one.

July is unpartitioned, fully feasible on capacity, and has 48 demanded PCR GTs. August is a forward order book, arithmetically infeasible by ~3.2 points, partitioned, with 73 demanded PCR GTs. Two flags tuned on July alone were found on 13 August to cost August real fulfilment (WARM_PRESS: Jul +0.6 / Aug −0.5; T0_STOCK_BASIS=lot: Jul +0.1 / Aug TBR −0.7). Both were reverted. Nothing in this report should be acted on without re-checking it on August via scripts/ab_both_months.py.

# 1. Executive summary — the 15,309 PCR tyres, accounted for exactly

PCR finishes July at 96.2 % in-month, TBR at 95.7 %. The PCR gap is 15,309 tyres against gross demand of 398,405. The decomposition below sums to 15,309 — not approximately, exactly:

| Loss | PCR tyres | pt | Class | Owner |
| --- | --- | --- | --- | --- |
| Opening GT netted out of the build requirement, never credited as an in-month cure | 3,642 | 0.91 | Definitional | — |
| No feasible release — no R5-legal window on an allowable machine | 6,310 | 1.58 | Genuine scheduling + narrow matrices | Shared |
| min_lot floor would be breached | 2,232 | 0.56 | Policy | Plant ruling |
| Built in the tail window, after 07:00 on 31 Jul | 1,675 | 0.42 | Definitional | Plant ruling |
| B12 residual — GT demand below 300, never planned | 1,124 | 0.28 | Policy | Plant ruling |
| Closing GT left standing at 07:00 on 1 Aug | 313 | 0.08 | Definitional | — |
| Other L5 scheduling | 13 | 0.00 | Ours | — |
| TOTAL | 15,309 | 3.84 |  |  |

59 % of the gap is definitional or plant policy. 41 % — the 6,310 "no feasible release" line — is the genuinely recoverable share, and most of that is locked behind narrow allowable-machine matrices rather than behind the search.

The single most important finding:

There is no unexplained residue anywhere in the July plan. build_starved.parquet reconciles EXACTLY with the waterfall's unfed line — PCR 6,310 + 2,232 = 8,542; TBR 1,454 + 52 = 1,506. "The optimiser is bad" is not a supportable diagnosis for July.

Separately, and on a different lens: 6,372 PCR tyres are built in July and cure on 1–2 August. They are real output that the horizon rule excludes. If the plant rules that they count, PCR reads 97.8 %.

# 2. The waterfall — demand to completed, every step

Three relationships in net_requirement are counter-intuitive and were got wrong on the first pass of this analysis: net_cure == demand (opening GT is supply, not a demand deduction); fg_stock == 0; and `usable` counts opening-GT units, not resolved SKUs.

## PCR

| Stage | Qty | Delta | Why / who owns it |
| --- | --- | --- | --- |
| Demand (= plant's own July output) | 398,405 | — |  |
| − covered by opening GT on floor | 393,585 | −4,820 | Supply already standing |
| + cure-yield scrap uplift | 394,763 | +1,178 | HARD: yield 0.997 |
| L4.5 lot-sized gross build | 394,763 | 0 | == gross_build |
| L5 scheduled into cure campaigns | 393,626 | −1,137 | B12 residual dropped = 1,124 (POLICY) |
| L7 actually BUILT and fed | 385,084 | −8,542 | Building could not reach the seat in time |
| Built before 31 Jul 07:00 | 383,409 | −1,675 | Rest is tail-window |
| Cured IN-MONTH | 383,096 | −313 | Closing GT on floor |
| IN-MONTH FULFILMENT | 96.2 % |  | L11 reports 96.2 % — reconciles |
| Carry-out tail, cures in August | 6,372 |  | Real output the horizon rule excludes |

## TBR

| Stage | Qty | Delta | Why / who owns it |
| --- | --- | --- | --- |
| Demand (= plant's own July output) | 98,020 | — |  |
| − covered by opening GT on floor | 96,723 | −1,297 |  |
| + cure-yield scrap uplift | 98,545 | +1,822 | HARD: yield 0.982 |
| L4.5 lot-sized gross build | 98,545 | 0 |  |
| L5 scheduled into cure campaigns | 97,289 | −1,256 | B12 residual dropped = 554 (POLICY) |
| L7 actually BUILT and fed | 95,783 | −1,506 |  |
| Built before 31 Jul 07:00 | 95,047 | −736 |  |
| Cured IN-MONTH | 94,231 | −816 | Closing GT on floor |
| IN-MONTH FULFILMENT | 96.1 % |  | L11 reports 95.7 % — it divides by plannable (97,436), not gross demand |
| Carry-out tail | 2,006 |  |  |

# 3. The demerits — where we are worse than the plant

Ranked by how much they cost. "Plant" is the mined 242-day MES baseline in plant_profile.json.

| # | Demerit | Plant | Engine | Gap | Cost |
| --- | --- | --- | --- | --- | --- |
| 1 | PCR build changeovers/machine-day | 1.84 | 2.53 | +38 % | The clearest real demerit |
| 2 | PCR weighted CO min/machine-day | 74.0 | 78.7 | +6 % | ~35 machine-h of extra setup |
| 3 | PCR same-size share of build COs | 91.5 % | 82.3 % | −9.2 pt | Longer setups per switch |
| 4 | TBR presses used per GT | 6.35 mean / 4.0 p50 | 3.54 / 2.0 | −44 % | Genuinely narrow on TBR only |
| 5 | PCR daily output CV, interior days | 0.116 | 0.156 | +34 % | Month-start dip; smaller than first reported |
| 6 | GTs per machine-day (PCR) | 2.17 | 2.58 | +19 % | We spread each machine thinner |
| 7 | TBR fulfilment | 100 % | 95.7 % | −4.3 pt | Worse than PCR on an easier problem |
| 8 | PCR stickiness | 99.84 % | — | not matched | Plant almost never switches mid-run |
| 9 | cap_press omits 6 plant-sanctioned presses | 92 on roster | 86 visible | 6 presses | Real data defect — but see section 12 |
| 10 | PCR press utilisation vs physical roster | ~100 % | 89.8 % | 6,311 idle press-h | Mostly presses legal for only 2 GTs |

Three demerits in the first issue of this report were wrong and have been removed. They are documented in section 12 rather than deleted silently.

Where we already beat the plant

| Metric | Plant | Engine | Verdict |
| --- | --- | --- | --- |
| PCR daily output mean | 12,381 | 12,422 | We out-produce it per day |
| TBR weighted CO min/machine-day | 35.6 | 33.6 | Better |
| TBR same-size share | 100 % | 100 % | Matched |
| Mould changes per press-day | 0.08 / 0.04 | 0.04 / 0.03 | ~2× better |
| R5 shelf-life breaches | n/a | 0 | 100 % compliant |
| Allowable-machine violations | n/a | 0 | Was 19.9 % of volume pre-v9 |

# 4. Per-GT — where the loss concentrates

PCR loss is CONCENTRATED: the top 10 of 34 short GTs carry 65 % of it. TBR is SPREAD (top 10 of 39 = 53 %), which means TBR needs a systemic fix and PCR needs a per-GT one.

| GT (PCR) | Plant | Engine | Loss | Press e/p | Mach e/p | Flags |
| --- | --- | --- | --- | --- | --- | --- |
| GT 2258 RAN HPE | 12,897 | 10,849 | 2,048 | 4 / 15 | 1 / 8 | Press+machine underuse |
| GT 1513 XPC1 MSIL | 55,663 | 54,285 | 1,378 | 22 / 44 | 3 / 11 | Press+machine underuse |
| GT 1402 XPC TATA | 20,788 | 19,593 | 1,195 | 12 / 22 | 2 / 5 | Press+machine underuse |
| GT 1844 XPC TML | 11,181 | 10,446 | 735 | 7 / 16 | 2 / 11 |  |
| GT 2568 HT2 | 16,090 | 15,373 | 717 | 7 / 20 | 2 / 8 |  |
| GT 2267 ROYL HYU | 31,947 | 31,264 | 683 | 12 / 31 | 3 / 8 |  |
| GT 1995 ROYL KIA | 14,249 | 13,698 | 551 | 5 / 27 | 3 / 11 |  |
| GT 1765 ROYL | 21,359 | 20,813 | 546 | 8 / 21 | 3 / 11 |  |
| GT 1412 XPC MM | 5,238 | 4,793 | 445 | 3 / 11 | 2 / 5 |  |
| GT 1482 UHL | 20,630 | 20,223 | 407 | 8 / 12 | 3 / 5 |  |

GT 2258 RAN HPE is the clearest single target: we ran it on 1 machine of 8 capable and 4 presses of 15, and lost 2,048 tyres — 13 % of the whole PCR gap on one GT.

# 5. Are we over-constraining? — the AND-stack test

doc.txt asks whether the engine demands every preferred condition simultaneously where the plant says "if feasible, run it". That is the right question. Tested by classifying every filter:

| Filter | Class | Note |
| --- | --- | --- |
| Allowable building machine (R2) | HARD | Plant's own matrix |
| Allowable press (R3) | HARD | 0 violations both months |
| Mould concurrency ≤ mould count | HARD | Physical |
| PCR inch capability | HARD | Physical |
| TT/TL group split (B16) | HARD | Confirmed by plant |
| GT shelf life 72 h (R5) | HARD | Perishability |
| Build lot floor B12 150/70 | POLICY | Plant runs 12.7 % PCR / 30.8 % TBR sub-floor; we run 0.0 % |
| Min demand to plan 300/150 | POLICY | Plant makes these; we drop them |
| GT WIP rail G8 4800/1400 | POLICY | A rail, not a wall |
| Mined rim lock | PREFERENCE | Already OFF — measured −14 pt |
| Historical machine share | PREFERENCE | Already OFF — measured −0.4 pt |
| Same-rim / sister clustering | PREFERENCE | Tie-break only, never a veto |

VERDICT: 6 HARD + 3 POLICY. Every PREFERENCE filter is already shipped OFF after measurement, so the "stacked preferences create the ceiling" hypothesis does not hold for this engine as shipped. The recoverable set is the 3 POLICY rows — and all 3 are plant rulings, not code changes.

# 6. Eligibility funnel — we use about two-thirds of what we are allowed

| Stage | PCR | TBR | Note |
| --- | --- | --- | --- |
| Building machines — mined capability | 9.83 | 3.39 | MES history |
| … after plant allowable matrix (HARD) | 3.20 | 3.11 | R2 |
| … after rim lock | 3.20 | 3.11 | OFF, no effect |
| … after rim sets | 3.20 | 3.11 | OFF, no effect |
| ENGINE ACTUALLY USED | 2.17 | 2.50 | 68 % / 80 % of allowed |
| Presses — mined capability | 13.34 | 20.96 |  |
| … mould concurrency cap (HARD) | 8.49 | 7.70 | R3 |
| ENGINE ACTUALLY USED | 4.61 | 3.54 | 54 % / 46 % of legal |

The first issue of this report called the last row a demerit. That was wrong, and the correct comparator makes the opposite case:

| Breadth measure | PLANT actual | ENGINE | Verdict |
| --- | --- | --- | --- |
| PCR building machines per GT | 1.57 mean / 1.0 p50 | 2.17 / 2.0 | We are 38 % BROADER than the plant |
| TBR building machines per GT | 2.30 / 2.0 | 2.50 / 2.0 | Broader |
| PCR presses per GT | 5.87 mean / 2.0 p50 | 4.61 / ++3.0 | Broader on the median, narrower on the mean |
| TBR presses per GT | 6.35 / 4.0 | 3.54 / 2.0 | Genuinely narrower — the one real gap |

Comparing what we use against the ALLOWABLE CEILING (3.20 machines, 8.49 presses) manufactures a demerit that does not exist. The plant itself uses 1.57 machines per SKU on PCR. Breadth is not a virtue — the plant is narrower than us and beats us. The only genuine breadth gap is TBR curing presses.

Breadth is also not free: 8 of 9 breadth-style experiments have measured negative (rim grouping −25,549 tyres; machine share −0.4 pt; de-pinning −0.5 pt), and the press-matrix union tested for this review reduced BUILT output on both months (section 12).

# 7. Lot sizing, changeovers, presses, inventory

## Lot sizing — the comparison that looks alarming and is not

| Measure | PCR plant | PCR engine | TBR plant | TBR engine |
| --- | --- | --- | --- | --- |
| Build run / slice p50 | 367 | 157 | 82 | 26 |
| Build changeovers per machine-day | 1.84 | 2.53 | 3.12 | 3.22 |
| Distinct GTs per machine-day | 2.17 | 2.58 | 3.02 | 3.34 |
| Weighted CO min per machine-day | 74.0 | 78.7 | 35.6 | 33.6 |

The p50 row is NOT apples to apples and should not be quoted. Our build SLICE is the third campaign level (cure campaign → build run → build slice); consecutive same-GT slices on one machine are one physical run and cost no changeover. The honest measure is changeovers per machine-day, where we are 38 % worse than the plant on PCR and roughly level on TBR.

## Press utilisation

| Plant | Denominator | Running | Mould change | IDLE |
| --- | --- | --- | --- | --- |
| PCR | 86 presses the engine was offered | 61,436 h (96.0 %) | 701 h (1.1 %) | 1,848 h (2.9 %) |
| PCR | 92 presses on the PHYSICAL roster | 61,436 h (!!89.8 %) | 701 h (1.0 %) | 6,311 h (9.2 %) |
| TBR | 79 offered / 80 roster | 57,068 h (97.1 %) | 535 h (0.9 %) | 1,172 h (2.0 %) |

Both PCR rows are true and the second is the honest one. Grading ourselves against the 86 presses the engine was handed proves only that the planner agrees with its own inputs — the same failure mode the project bans for verifiers. Against the physical roster of 92, PCR press utilisation is 89.8 %. The 6-press gap is a master-data defect (section 12), though those presses are plant-legal for only 2 GTs.

Two denominator traps were hit while producing these and are worth recording: cycle_time_curing lists 92 PCR / 80 TBR presses against a roster of 86 / 79 (using the master inflated PCR idle from 2.9 % to 7.3 % and invented "6 unused presses"), and campaign hours must be clipped to the horizon or tail campaigns push TBR above 100 % utilisation. This is the same class as the four denominator defects already in the project ledger.

## GT inventory — we have the opposite of the problem doc.txt describes

| Plant | GT built | GT cured | Net | Time-wtd inventory | Rail |
| --- | --- | --- | --- | --- | --- |
| PCR | 385,084 | 385,084 | 0 | 3,699 | 4,800 |
| TBR | 95,783 | 95,783 | 0 | 1,136 | 1,400 |

doc.txt's failure mode is "Building 100,000 / Curing 90,000 / GT +10,000 — you are producing what curing cannot consume". That is not our shape. Net is zero and inventory sits below the rail on both plants. Our problem is the mirror image: cure seats go unfilled because building could not reach them in time, not because building overproduced. Inventory is measured time-weighted, never event-weighted — event-weighting once biased TBR upward 5.7 %.

# 8. The rejection ledger — already instrumented, and it reconciles

doc.txt item 9 asks for a rejection reason on every scheduling decision. It already exists: build_starved.parquet and cure_unplaced.parquet carry a reason on every rejected lot, and decision_trace records the rule IDs behind each placement.

| Plant | Reason | Tyres | Lots |
| --- | --- | --- | --- |
| PCR | No feasible release | 6,310 | 40 |
| PCR | Would breach min_lot | 2,232 | 22 |
| PCR | TOTAL | 8,542 | 62 |
| TBR | Would breach min_lot | 1,454 | 58 |
| TBR | Below min_lot (strict B12) | 52 | 2 |
| TBR | Cure remainder past horizon | 621 | 2 |
| TBR | TOTAL build-side | 1,506 | 60 |

These reconcile EXACTLY with the waterfall's unfed line — PCR 6,310 + 2,232 = 8,542; TBR 1,454 + 52 = 1,506. There is no unexplained residue anywhere in the July plan.

# 9. The scorecard

| Metric | PCR plant | PCR engine | TBR plant | TBR engine |
| --- | --- | --- | --- | --- |
| Demand | 398,405 | 398,405 | 98,020 | 98,020 |
| Production, in-month | 398,405 | 383,096 | 98,020 | 94,231 |
| Production + carry-out tail | 398,405 | 389,468 | 98,020 | 96,237 |
| Fulfilment % | 100.0 | 96.2 | 100.0 | 95.7 |
| Daily output mean | 12,381 | 12,422 | 3,101 | 3,090 |
| Daily output CV | 0.116 | 0.267 | 0.142 | 0.291 |
| Build COs per machine-day | 1.84 | 2.53 | 3.12 | 3.22 |
| Weighted CO min/machine-day | 74.0 | 78.7 | 35.6 | 33.6 |
| GTs per machine-day | 2.17 | 2.58 | 3.02 | 3.34 |
| Presses used | 86 | 86 | 79 | 79 |
| Press utilisation % | ~100 | 96.0 | ~100 | 97.1 |
| Same-size share of build COs | 91.5 % | 82.3 % | 100 % | 100 % |
| GT wait max (R5 ≤ 72 h) | — | 70.9 h | — | 72.0 h |

# 10. What to correct — ranked, with owner

## Plant rulings (largest value, no code)

| # | Item | Worth (Jul) | Question for the plant |
| --- | --- | --- | --- |
| 1 | Narrow allowable-machine matrices | Largest single item | 26 of 73 Aug PCR GTs have ≤2 allowable machines; TBMPCR7 lists 39 GTs against TBMPCR2's 130. Can any be widened? |
| 2 | Horizon ruling — does the carry-out tail count? | +1.60 pt PCR / +2.05 pt TBR | 6,372 PCR tyres are built in July and cure on 1–2 Aug. Real output; currently excluded. |
| 3 | B12 sub-floor ruling | +0.56 pt PCR / +1.48 pt TBR | The plant itself runs 12.7 % PCR / 30.8 % TBR sub-floor. We run 0.0 %. May we match the plant? |
| 4 | B12 residual (min demand 300/150) | +0.28 pt PCR / +0.57 pt TBR | 1,124 PCR / 554 TBR tyres are never planned. The plant makes them. |
| 5 | 30-June machine state — 20 rows | Part of the day-1 dip | Which GT was each of the 11 PCR / 9 TBR machines building at 07:00 on 1 July? |
| 6 | Opening-stock GT spread | Part of the day-1 dip | Quantity is verified correct by Little's law, but it sits on only 25 of 48 demanded PCR GTs. |

## Engineering (ours, and honest about the odds)

| # | Item | Est. worth | Confidence |
| --- | --- | --- | --- |
| 7 | Targeted second-pass repair on the 34 short PCR GTs — re-offer unfed lots to idle, allowable, R5-legal machine windows | ≤ 0.6 pt | Medium — 222 R5-legal idle hours exist, but only ~9 % of idle time is legally usable |
| 8 | GT 2258 RAN HPE specifically — 1 machine of 8, 4 presses of 15 | up to 2,048 tyres | Medium — worth a single-GT investigation first |
| 9 | Month-start dip — CV 0.267 vs plant 0.116 | ~3.3k tyres | Low — six approaches measured, one gained 0.3 pt and it then failed the August gate |
| 10 | July partition (none exists; July runs unpartitioned) | ~0.6 pt + same-size | Blocked — needs the raw MES drop |

What NOT to do

Do not build before 07:00 on 1 July ("carry-in"). It borrows June's capacity and is not ours to spend.

Do not relax min_lot, min_demand, or the R5 shelf life to buy fulfilment. Those are the plant's caps; changing them changes the answer, not the plan.

Do not halve setup times. The same objection applies.

Do not re-enable the rim lock, machine-share ordering, or depth-before-breadth queue order. All measured negative (−14 pt, −0.4 pt, −11.9 pt).

Do not tune anything on July alone. Two flags did exactly that and cost August real fulfilment.

# 11. Method notes — defects found while producing this report

Recorded because this project's most productive bug class is the measurement, not the scheduler. Four denominator defects were already in the ledger; this analysis added four more, all mine, all caught before they reached a conclusion:

A sweep harness summed qty_fed_in_month — the FED basis, which includes opening stock — and reported it as in-month. Inflated July by ~0.6 pt and reversed the sign of a PCR/TBR comparison. The harness is retired.

The first waterfall assumed net_cure = demand − opening and that `usable` counted resolved SKUs. Both wrong: net_cure == demand, and `usable` counts opening-GT units.

In-month output was computed as built − tail. Closing stock is not the carry-out tail; the correct form is a horizon cut on the ledger. The wrong form overstated TBR by 1.3 pt.

Press utilisation used cycle_time_curing's 92/80 press count against a roster of 86/79, and did not clip campaign hours to the horizon. PCR idle read 7.3 % instead of 2.9 %, with six phantom unused presses.

Every figure in this report is regenerated by scripts/diag_plant_vs_engine.py from the run artefacts. If the plan changes, re-run it rather than editing this document.

# 12. Expert review of this report — what it got wrong

This section exists because the first issue of this document shipped three wrong demerits and nearly recommended a change that reduces production. The corrections are more useful than the original claims.

## Corrected: three demerits that were not demerits

| Original claim | What was wrong | Corrected |
| --- | --- | --- |
| "PCR machines per GT 2.17 vs 3.20 allowable = 68 % — underuse" | Compared against the ALLOWABLE CEILING, not against the plant. The plant itself uses 1.57 machines per SKU. | We are 38 % BROADER than the plant. Not a demerit. |
| "Presses per GT 4.61 vs 8.49 mould-legal = 54 % — underuse" | Same error. Plant PCR actual is 5.87 mean but 2.0 median. | PCR: broader than plant on the median (3.0 vs 2.0). TBR is the one genuine gap (3.54 vs 6.35). |
| "Daily output CV 0.267 vs plant 0.116 — 2.3× worse" | Computed on WALL-CLOCK dates, not plant-days, and included two partial boundary days. | PCR interior CV is 0.156 vs 0.116 — real but a third of the claimed size. ++TBR is 0.113 vs plant 0.142: we are STEADIER. |

## Corrected: the press-utilisation denominator, in both directions

The first issue used 92 presses, then "fixed" it to 86 on the strength of a doc. Both were wrong to state alone. 92 is the physical roster (four independent masters agree); 86 is what cap_press_2026-07 offers the engine. Grading against 86 proves only that the planner agrees with its own inputs.

## New finding: 6 plant-sanctioned presses are invisible to the planner

cap_press_2026-07 is MINED from MES. allowed_press_matrix is the PLANT'S OWN file and is broader. PCR presses 17–22 are physically present (132 tyres/day each) and marked `direct` by the plant for GT 1402 XPC TATA and GT 1412 XPC MM — two of the three largest per-GT losses. L5 gates on cap_press, so it never sees them. Mould headroom exists (GT 1402: 20 moulds, 12 presses used), so R3 does not block it.

This is the exact converse of the v9 building-machine fix. There the plant matrix was NARROWER than mined capability and became a hard restrict. Here it is BROADER, so it would be a union — and nobody checked that direction, because the press gate was verified only for violations ("0 violations, clean") and never for omissions. A gate can be clean and still be costing you output.

## …and why the fix was still REJECTED

Implemented and measured on both months. Reading in-month fulfilment alone, it is the biggest win of the project: August PCR 91.4 % → 94.8 %. It is not a win.

| Arm | BUILT | In-month | Carry-out tail | TOTAL real output |
| --- | --- | --- | --- | --- |
| Aug, union OFF | 410,652 | 392,239 (91.4 %) | 23,381 | 415,620 (96.8 %) |
| Aug, union ON | 408,220 | 406,830 (94.8 %) | 6,616 | 413,446 (96.3 %) |
| Jul, union OFF | 385,084 | 383,266 (96.2 %) | 6,372 | 389,638 (97.8 %) |
| Jul, union ON | 378,838 | 382,070 (95.9 %) | 1,290 | 383,360 (96.2 %) |

The union BUILDS FEWER TYRES on both months (−2,432 August, −6,246 July) and total real output FALLS on both. Every point of the apparent August gain is the carry-out tail moving inside the horizon — cures happen earlier, not more. Mechanism: more eligible presses → more parallel campaigns → building feeds more GTs at once → same-size share 75.2 % → 69.5 % (an L11 invariant flips PASS→FAIL) and weighted changeover 99.8 → 107.2 min/machine-day.

THE LESSON, which generalises well past this flag: in-month fulfilment is TAIL-SENSITIVE. Any change that pulls cures earlier inflates it without producing anything. BUILT and in-month+tail must be reported alongside it. A change that moves in-month while BUILT falls is relocating output, not creating it.

The code ships behind PLANNER_PRESS_FROM_MATRIX, defaulting OFF, with the measurement recorded in l5_cure_master.py. The underlying master defect is real and stands; it is simply not worth exploiting today.

## What this changes about the recommendations

The August headline (91.4 %) is substantially DEFINITIONAL. On total real output August is ~96.8 %, close to July's 97.8 %. The apparent 5-point August deficit is mostly a 23,381-tyre carry-out tail, not lost production.

The horizon ruling (section 10, item 2) is therefore worth far more on August than on July — 23,381 tyres against 6,372. It should be the first question put to the plant.

Breadth is dead as an improvement direction. The plant is narrower than us and beats us; every breadth experiment including this one has measured negative on BUILT.

The remaining engineering item is unchanged and modest: a targeted repair pass on the 6,310 "no feasible release" tyres, graded on BUILT.

# 13. August 2026 — the ">95 %" question, answered

Asked directly: can August come in above 95 % fulfilment? The honest answer depends entirely on which of the three numbers is meant, and two of the three already clear it.

| August | Demand | BUILT | built % | In-month | in-month % | Tail | In-month + tail | total % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PCR | 429,146 | 410,652 | 95.7 % | 392,239 | 91.4 % | 23,381 | 415,620 | 96.8 % |
| TBR | 99,019 | 92,541 | 93.5 % | 88,523 | 89.4 % | 3,517 | 92,040 | 93.0 % |

PCR already clears 95 % on production (95.7 %) and on total real output (96.8 %). It does not on in-month (91.4 %), and TBR clears it on none.

## Nine arms were swept trying to lift in-month. None reached 95 %.

| Arm | BUILT | ΔBUILT | In-month | ful % | L11 |
| --- | --- | --- | --- | --- | --- |
| base (shipped) | 410,652 | — | 392,239 | 91.4 | 27/42 |
| HORIZON_MODE=strict | 380,080 | −30,572 | 384,944 | 89.7 | 25/42 |
| HORIZON_MODE=truncate | 384,156 | −26,496 | 388,806 | 90.6 | 26/42 |
| HORIZON_MODE=window | 393,182 | −17,470 | 389,665 | 90.8 | 27/42 |
| HORIZON_TAIL_H=48 | 403,762 | −6,890 | 391,810 | 91.3 | 26/42 |
| HORIZON_TAIL_H=24 | 393,800 | −16,852 | 391,381 | 91.2 | 26/42 |
| PRESS_FROM_MATRIX=1 | 408,220 | −2,432 | 406,830 | 94.8 | 26/42 |
| TAIL_H=24 + PRESS | 404,061 | −6,591 | 405,543 | 94.5 | 24/42 |
| TAIL_H=0 + PRESS | 399,316 | −11,336 | 404,256 | 94.2 | 25/42 |

The August PCR in-month ceiling is ~94.8 %, and every arm that lifts in-month cuts BUILT. Cause: about 14,400 PCR tyres are BUILT after 07:00 on 1 September under the default 72-hour extension. Shortening the extension does not move them inside the month — it deletes them. BUILT falls faster than in-month rises.

## The two honest routes above 95 %, both plant rulings

| Route | Effect | Basis |
| --- | --- | --- |
| Horizon ruling — does the carry-out tail count? | Aug PCR 91.4 % → 96.8 % | 23,381 tyres are already built and cure 1–3 Sep. No code change. |
| B12 sub-floor ruling on TBR | Aug TBR +6.2 pt | 6,100 tyres over 225 lots are rejected by min_lot. The plant itself runs 30.8 % of TBR sub-floor; we run 0.0 %. |
| TBR allowable matrix (still unresolved from v9) | Aug TBR ~+5 pt | The plant's TBR file is tighter than the derived list for August's 37 GTs. Needs a ruling on which is authoritative. |

What was NOT done, and will not be: the in-month number was not manufactured by relaxing min_lot, min_demand, the 72-hour shelf life or setup times, and no tyre was built before the month opened. Each of those raises the KPI without the plant making a single extra tyre.